RACI MATRIX

Delivery Manager vs Program Manager

Taazaa Inc. | Delivery Organization

February 2026

# Purpose

This document resolves the role overlap between the Delivery Manager (DM) and Program Manager (PgM) by mapping every key activity to a single accountable owner. Both roles operate at the Owner level of the COL framework, but they serve fundamentally different purposes.

| Role | Primary Lens | Core Question They Answer |
| --- | --- | --- |
| Delivery Manager | Account / Client (vertical) | Is this client's delivery healthy, profitable, and predictable? |
| Program Manager | Program / Strategic (horizontal) | Are these interconnected projects delivering the intended business outcome together? |

## How to Read RACI

| Code | Meaning | Rule |
| --- | --- | --- |
| R | Responsible | Does the work or drives execution |
| A | Accountable | Single owner of the outcome; final decision authority |
| C | Consulted | Provides input before decisions are made |
| I | Informed | Kept in the loop after decisions are made |

Rule: Every activity has exactly ONE 'A'. Multiple 'R's are allowed.

## Roles Referenced

| Abbreviation | Role | COL Level |
| --- | --- | --- |
| DoD | Director of Delivery | Leader |
| DM | Delivery Manager | Owner |
| PgM | Program Manager | Owner |
| PM | Project Manager | Owner |

# 1. Strategy & Planning

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Define delivery strategy and operating model | A | C | C | I |
| 1.2 | Align program objectives to company OKRs/vision | C | I | A/R | I |
| 1.3 | Define program roadmap and success metrics (KPIs) | I | C | A/R | C |
| 1.4 | Define account-level delivery strategy | C | A/R | I | C |
| 1.5 | Capacity planning aligned to sales pipeline | A | R | C | I |
| 1.6 | Program-level resource allocation across competing initiatives | C | C | A/R | I |
| 1.7 | Account-level resource and bench planning | C | A/R | I | R |
| 1.8 | Define delivery governance framework (Agile/SAFe/Hybrid) | A/R | C | C | I |
| 1.9 | Tailor governance cadence to specific program needs | I | C | A/R | R |

KEY DISTINCTION: The PgM sets the strategic direction for a program (what outcomes, which KPIs, how projects connect). The DM sets the account delivery strategy (how to keep this client healthy and profitable). The DoD sets the organizational delivery strategy.

# 2. Delivery Execution & Oversight

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 2.1 | End-to-end project execution (sprints, ceremonies, backlogs) | I | I | I | A/R |
| 2.2 | On-time delivery of individual projects | I | C | C | A/R |
| 2.3 | On-time delivery of program milestones (cross-project) | I | C | A/R | R |
| 2.4 | Account-level delivery predictability (across all projects for a client) | C | A/R | C | R |
| 2.5 | Scope adherence and change request enforcement (project level) | I | C | I | A/R |
| 2.6 | Scope alignment to program objectives (cross-project) | I | I | A/R | C |
| 2.7 | Sprint planning, RAID log maintenance, Jira hygiene | I | I | I | A/R |
| 2.8 | Cross-project dependency identification and resolution | I | C | A/R | R |
| 2.9 | Cross-account dependency and trade-off management | A | R | C | I |
| 2.10 | SLA adherence and quality compliance | C | A | C | R |
| 2.11 | Delivery governance reviews and steering committees (account) | C | A/R | C | R |
| 2.12 | Program-level governance reviews and decision forums | C | C | A/R | R |

KEY DISTINCTION: The PM executes project delivery. The PgM ensures cross-project dependencies and milestones are on track. The DM ensures all delivery for an account is predictable and the client is never surprised. The DoD intervenes only for systemic or portfolio-level issues.

# 3. Financial Management

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Project-level P&L tracking (GM%, burn rate) | I | C | I | A/R |
| 3.2 | Account-level financial performance (revenue, margin, billing) | C | A/R | I | R |
| 3.3 | Program-level budget management and forecasts | C | C | A/R | R |
| 3.4 | Portfolio-level P&L and margin optimization | A/R | R | C | I |
| 3.5 | Billing milestone tracking and realization (>95%) | I | A | I | R |
| 3.6 | Change request commercial management | I | A | C | R |
| 3.7 | Cost efficiency and utilization optimization (account) | C | A/R | I | R |
| 3.8 | Resource cost optimization across program initiatives (ROI) | C | C | A/R | I |
| 3.9 | Program value realization and ROI tracking | I | I | A/R | C |
| 3.10 | Monthly P&L review with Finance & Delivery Head | C | A/R | C | R |
| 3.11 | Budget variance analysis and corrective action (program) | C | C | A/R | R |

KEY DISTINCTION: The PM owns project-level P&L. The DM owns account-level commercial outcomes (billing, margin, revenue across all projects for that client). The PgM owns program-level budget and ROI (value delivered vs. invested across interconnected projects). The DoD owns the portfolio.

# 4. Risk Management

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Project-level RAID log maintenance | I | I | I | A/R |
| 4.2 | Cross-project risk and dependency identification | I | C | A/R | R |
| 4.3 | Account-level risk anticipation (delivery + commercial) | C | A/R | C | R |
| 4.4 | Program-level risk mitigation (before escalation) | C | C | A/R | R |
| 4.5 | Escalation to leadership with options (not problems) | I | C | A/R | C |
| 4.6 | Account-level escalation management (client-facing) | C | A/R | C | I |
| 4.7 | Final escalation authority for delivery risks | A/R | C | C | I |
| 4.8 | Systemic risk resolution (patterns across accounts) | A/R | R | C | I |
| 4.9 | Program dependency map creation and maintenance | I | I | A/R | C |
| 4.10 | Risk scanning and early-warning dashboards | I | C | A/R | R |

KEY DISTINCTION: The PM catches risks at the project level. The PgM catches risks that span across projects within a program (dependencies, conflicts). The DM catches risks that threaten client satisfaction or account commercial health. The DoD catches systemic or portfolio-wide patterns.

# 5. Client & Stakeholder Management

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Day-to-day client communication on project status | I | I | I | A/R |
| 5.2 | Account-level client confidence and satisfaction (CSAT >= 4.5) | C | A/R | C | R |
| 5.3 | Executive-level client relationship management | A/R | R | I | I |
| 5.4 | Primary escalation point for delivery issues (account) | C | A/R | C | R |
| 5.5 | Program-level stakeholder updates (executives & sponsors) | I | I | A/R | C |
| 5.6 | Steering committee and governance reviews (account) | C | A/R | C | R |
| 5.7 | Program decision forums and executive alignment | C | I | A/R | I |
| 5.8 | SOW scoping, estimation support, and deal shaping | C | R | C | R |
| 5.9 | Complex deal shaping and project recovery (pre-sales) | A/R | R | C | I |
| 5.10 | Weekly dashboards (P&L, risks, delivery health) | I | C | C | A/R |
| 5.11 | Decision-oriented dashboards for leadership | C | C | A/R | R |
| 5.12 | Transparent communication to all stakeholders (program) | I | I | A/R | R |

KEY DISTINCTION: The PM publishes project-level status. The DM owns client relationship and satisfaction -- the client knows the DM's name and trusts them. The PgM owns internal stakeholder alignment -- ensuring executives and sponsors see how the program delivers business value. The DoD manages executive-level relationships and complex deal recovery.

# 6. People, Team & Capacity

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Team engagement, retention actions, attrition control (<10%) | I | A | I | R |
| 6.2 | Hiring demand raising and backfill (SLA <30 days) | I | A | I | R |
| 6.3 | Onboarding and ramp-up readiness | I | A/R | I | R |
| 6.4 | Performance management of delivery teams | C | A/R | I | R |
| 6.5 | Mentoring and developing Project Managers | C | A/R | R | I |
| 6.6 | Coaching PMs for delivery predictability (program context) | I | C | A/R | I |
| 6.7 | Cross-functional team alignment under a program | I | I | A/R | R |
| 6.8 | Resource conflict resolution across programs | C | C | A/R | I |
| 6.9 | Appraisal effectiveness and budget utilization | C | A | I | R |
| 6.10 | Succession planning and leadership bench building | A/R | R | C | I |
| 6.11 | 360-degree feedback process | C | A | C | R |
| 6.12 | Driving psychological safety and team culture | I | A/R | C | R |

KEY DISTINCTION: The DM is the people owner -- responsible for hiring, retention, engagement, performance, and developing PMs as individuals. The PgM coaches PMs in the context of program outcomes and resolves resource conflicts across projects. The DM asks 'Is this person growing and engaged?' The PgM asks 'Is this PM delivering what the program needs?'

# 7. Governance, Process & Continuous Improvement

| # | Activity | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Establish and enforce program governance cadence | I | C | A/R | R |
| 7.2 | Enforce delivery governance, metrics, and reporting (account) | C | A/R | C | R |
| 7.3 | Standardize delivery frameworks across the org | A/R | C | C | I |
| 7.4 | Define escalation paths and decision structures (program) | I | C | A/R | I |
| 7.5 | Drive continuous improvement through retrospectives | I | C | A/R | R |
| 7.6 | Identify and implement process improvements (account) | C | A/R | C | R |
| 7.7 | Lead adoption of new tools, processes, or systems | C | C | A/R | R |
| 7.8 | AI-enabled governance (status automation, risk scanning) | C | C | R | A/R |
| 7.9 | Replace status reports with decision dashboards | I | C | A/R | R |
| 7.10 | Delivery transformation and scale initiatives | A/R | R | R | I |

KEY DISTINCTION: The PgM is the change agent -- driving adoption of new processes, tools, and improvements across the program. The DM enforces existing governance within accounts and identifies account-specific improvements. The DoD drives org-wide transformation.

# 8. Artifacts Ownership

| # | Artifact | DoD | DM | PgM | PM |
| --- | --- | --- | --- | --- | --- |
| 8.1 | Project Plan & Sprint Receipts | I | I | I | A/R |
| 8.2 | Project-level RAID Log | I | I | I | A/R |
| 8.3 | Weekly Health Dashboard (RAG + P&L + attrition) | I | C | I | A/R |
| 8.4 | P&L Tracker (monthly, project level) | I | C | I | A/R |
| 8.5 | Billing vs. Burn Dashboard | I | A | I | R |
| 8.6 | Attrition & Retention Report | I | A/R | I | R |
| 8.7 | Backfill Tracker with SLA Adherence | I | A/R | I | R |
| 8.8 | Account Governance Review Deck | C | A/R | I | R |
| 8.9 | Program Roadmap | I | I | A/R | C |
| 8.10 | Program-level Risk Register | I | I | A/R | R |
| 8.11 | Cross-Project Dependency Map | I | I | A/R | C |
| 8.12 | Program RACI Matrix | I | C | A/R | C |
| 8.13 | Change Management Plan | I | C | A/R | R |
| 8.14 | Program Budget Report (budget vs. value) | I | C | A/R | R |
| 8.15 | Program Dashboard / Scorecard | C | I | A/R | R |
| 8.16 | Decision Dashboard for Leadership | C | C | A/R | R |
| 8.17 | Delivery Operating Model Documentation | A/R | C | C | I |

# Interaction Model: How DM and PgM Work Together

## When Both Roles Exist on the Same Engagement

Consider a client account "Acme Corp" running a "Digital Transformation" program with three projects: Mobile App, API Platform, and Data Migration.

| Aspect | Delivery Manager (DM) | Program Manager (PgM) |
| --- | --- | --- |
| Scope | Entire Acme Corp account (all programs, all projects) | Digital Transformation program (cross-project) |
| Owns | Client relationship, account P&L, team health, hiring | Cross-project dependencies, program milestones, OKR alignment, program ROI |
| Key Question | "Is Acme happy? Are we profitable? Are people retained?" | "Are Mobile App, API Platform, and Data Migration delivering the transformation outcome together?" |
| Reports To | Director of Delivery | Director of Delivery |
| Works With | PgM (for program context), PMs (for project status) | DM (for client/account impact), PMs (for execution) |

## Decision Rights Summary

| Decision Scenario | Who Decides | Who Is Consulted |
| --- | --- | --- |
| Should we extend the client's SOW? | DM | PgM, PM |
| Which project gets the shared resource this sprint? | PgM | DM, PMs |
| A PM is underperforming -- what action to take? | DM | PgM (for program context) |
| Program milestone needs to shift by 2 weeks | PgM | DM (for client impact) |
| Client is unhappy with delivery quality | DM | PgM, PM |
| We need to re-prioritize across programs | DoD | DM, PgM |
| A new tool should be adopted across the program | PgM | DM, PMs |
| Hiring demand for backfill on the account | DM | PgM, PM |
| Cross-project dependency is blocking 2 projects | PgM | PMs |
| Account attrition is trending above 10% | DM | DoD, PgM |

# Escalation Ladder

Level 1:  PM escalates to PgM (cross-project issue) OR to DM (account/client/people issue)

Level 2:  PgM escalates to DM (account impact) OR DM escalates to PgM (program alignment)

Level 3:  Both escalate to Director of Delivery

Level 4:  DoD escalates to CDO / CXO

| Escalation Type | First Point of Escalation | Final Authority |
| --- | --- | --- |
| Cross-project dependency conflict | PgM | DoD |
| Client dissatisfaction / relationship risk | DM | DoD |
| Resource conflict across programs | PgM | DoD |
| Account P&L deterioration | DM | DoD |
| Program not delivering strategic value | PgM | DoD |
| Team attrition / engagement crisis | DM | DoD |
| Systemic delivery failure | DoD | CDO |

# Summary: One-Line Differentiation

| Role | One-Line Accountability |
| --- | --- |
| Project Manager | My project ships on time, on budget, on quality. |
| Program Manager | My projects work together to deliver the strategic outcome. |
| Delivery Manager | My client is happy, my account is profitable, my people are thriving. |
| Director of Delivery | Delivery scales across all accounts without depending on heroes. |